## Report 3 (Technical Report)
| Report 3 |  |  |  |  | Project start: | [7 empty] | 2025-03-12
| Group 8 |  |  |  |  | Display week: | [7 empty] | 1
[6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31
| TASK | ASSIGNED TO | PROGRESS | START | END | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Document Design Template | Antonio Vallarta | 100% | 2025-03-12 | 2025-03-15
| Front Matter | Abdullah | 100% | 2025-03-15 | 2025-03-17
| Client Background | Tanuj | 100% | 2025-03-17 | 2025-03-21
| Develop charter | Vidit | 100% | 2025-03-21 | 2025-03-26
Planning and design
| Problem Definition (goals problems etc.) | Antonio Vallarta | 0% | 2025-03-11 | 2025-03-15
| Technical Description | Tanuj | 0% | 2025-03-13 | 2025-03-18
| Method of Assessment | Abdullah | 0% | 2025-03-18 | 2025-03-21
| Results | Vidit | 0% | 2025-03-18 | 2025-03-20
Execution
| Discussion | Antonio Vallarta | 0% | 2025-03-27 | 2025-04-01
| Recommendation | Abdullah | 0% | 2025-04-02 | 2025-04-05
| Conclusion | Tanuj | 0% | 2025-04-02 | 2025-04-06
| References | Vidit | 0% | 2025-04-05 | 2025-04-06
Evaluation
| Appendices | Antonio Vallarta | 0% | 2025-03-29 | 2025-04-01
| Revising and Editing | Abdullah | 0% | 2025-04-01 | 2025-04-05
| Final Proofread | Tanuj | 0% | 2025-04-05 | 2025-04-06
| Time to Rehearse/Record as Relevant | Vidit | 0% | 2025-04-03 | 2025-04-06
Team Skills
Team Member |  | Category 1 | Category 2 | Category 3
Antonio |  | Outlining & Organizing | Document Design & Formatting | Leadership - Organization & Delegation
Abdullah |  | Revising, Editing & Proofreading | Drafting | Negotiation & Sociability
Tanuj |  | Researching & Note-Taking | Designing Presentations | Team Skills - Ideas & Analysis
Vidit |  | Public Speaking | Creating & Incorporating Graphics | Leadership - Respect & Focus
References
[1] SIMPLE GANTT CHART by Vertex42.com https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html

## Progress Report - Presentation
| Progress Report |  |  |  |  | Project start: | [7 empty] | 2025-03-17
| Group 8 |  |  |  |  | Display week: | [7 empty] | 1
[6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07
| TASK | ASSIGNED TO | PROGRESS | START | END | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Presentation Format | Antonio Vallarta | 0% | 2025-03-17 | 2025-03-20
| Assign sections and speakers. | Abdullah | 0% | 2025-03-18 | 2025-03-19
Slide Deck Creation
| Design presentation template. | Antonio Vallarta | 0% | 2025-03-20 | 2025-03-22
| Draft slides for each section | Tanuj | 0% | 2025-03-22 | 2025-03-27
| Include visuals & graphics. | Abdullah | 0% | 2025-03-27 | 2025-03-30
| Proofread | Vidit | 0% | 2025-03-27 | 2025-03-29
Practice & Rehearsals
| Each team member practices their segment. | Everyone | 0% | 2025-04-01 | 2025-04-06
| Conduct a full team run-through. | Everyone | 0% | 2025-04-07 | 2025-04-10
| Adjust slides based on team feedback. | Vidit | 0% | 2025-04-07 | 2025-04-11
| References | Tanuj | 0% | 2025-04-10 | 2025-04-11
Final Recording/Edits
| Record final presentation (if applicable). | Antonio Vallarta | 0% | 2025-04-03 | 2025-04-06
| Make final adjustments based on rehearsals. | Abdullah | 0% | 2025-04-06 | 2025-04-10
| Final Proofread | Tanuj | 0% | 2025-04-10 | 2025-04-11
| Submission | Vidit | 0% | 2025-04-08 | 2025-04-11
Team Skills
Team Member |  | Category 1 | Category 2 | Category 3
Antonio |  | Organizing Slide Structure | Team Coordination | Ensuring Logical Flow of Content
Abdullah |  | Revising & Editing Slides | Scripting Narration | Handling Q&A Session
Tanuj |  | Designing Presentation | Creating Visuals & Graphics | Ensuring Clarity & Simplicity
Vidit |  | Public Speaking | Practicing Delivery | Engaging Audience Effectively
References
[1] SIMPLE GANTT CHART by Vertex42.com https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html

## Investigation
| Report 3 |  |  |  |  | Project start: | [7 empty] | 2025-03-12
| Group 8 |  |  |  |  | Display week: | [7 empty] | 1
[6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31
| TASK | ASSIGNED TO | PROGRESS | START | END | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Define Investigation Scope
| Identify key research questions. | Antonio Vallarta | 0% | 2025-03-12 | 2025-03-15
| Finalize research methodology. | Abdullah | 0% | 2025-03-15 | 2025-03-17
| Assign responsibilities for data collection. | Tanuj | 0% | 2025-03-17 | 2025-03-21
| Develop charter | Vidit | 0% | 2025-03-21 | 2025-03-26
Data Collection & Research
| Conduct literature review. | Antonio Vallarta | 0% | 2025-03-11 | 2025-03-15
| Gather experimental/test data. | Tanuj | 0% | 2025-03-13 | 2025-03-18
| Conduct interviews/surveys (if applicable). | Abdullah | 0% | 2025-03-18 | 2025-03-21
| Analyze collected data. | Vidit | 0% | 2025-03-18 | 2025-03-20
Preliminary Findings & Evaluation
| Organize findings into categories. | Antonio Vallarta | 0% | 2025-03-25 | 2025-03-27
| Compare results against initial research questions. | Abdullah | 0% | 2025-03-28 | 2025-03-30
| Identify any data gaps or issues. | Tanuj | 0% | 2025-03-28 | 2025-03-31
| References | Vidit | 0% | 2025-03-30 | 2025-03-30
Refining & Finalizing Analysis
| Validate research findings. | Antonio Vallarta | 0% | 2025-03-27 | 2025-03-30
| Adjust design or recommendations if needed. | Abdullah | 0% | 2025-03-30 | 2025-04-03
| Prepare summary of research for the report. | Tanuj | 0% | 2025-04-03 | 2025-04-04
| Time to Rehearse/Record as Relevant | Vidit | 0% | 2025-04-01 | 2025-04-04
Team Skills
Team Member |  | Category 1 | Category 2 | Category 3
Antonio |  | Structuring Research Plan | Managing Timeline & Milestones | Task Delegation & Coordination
Abdullah |  | Conducting Literature Review | Data Collection & Analysis | Ensuring Research Accuracy
Tanuj |  | Technical Writing (Documenting Findings) | Evaluating Sources & Validating Data | Identifying Research Gaps
Vidit |  | Presenting Research Findings | Creating Charts & Visual Representations | Summarizing Key Takeaways
References
[1] SIMPLE GANTT CHART by Vertex42.com https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html